RTU MOBILE APPLICATION

Development Plan & Technical Blueprint

Riga Technical University

Prepared by: Parikshit Kaushal | Team Lead - Agentic AI & Web Development

Date: March 2026 | Version 1.0

# Table of Contents

1. Executive Summary  ........................................  3

2. Project Overview & Scope  ........................................  4

3. RTU Brand & Design Reference Strategy  ........................................  5

4. Technology Stack  ........................................  7

5. Application Architecture  ........................................  8

6. Feature Modules Breakdown  ........................................  10

7. Data & API Strategy (Mock-First Approach)  ........................................  14

8. Sprint Plan (8 Weeks)  ........................................  15

9. Team Allocation & Responsibilities  ........................................  18

10. Website-to-App Theme Extraction Process  ........................................  19

11. Quality Assurance & Testing Strategy  ........................................  21

12. Deliverables & Milestones  ........................................  22

13. Risk Assessment & Mitigation  ........................................  23

14. Post-Prototype Roadmap  ........................................  24

# 1. Executive Summary

This document outlines the comprehensive development plan for building a mobile application prototype for Riga Technical University (RTU). The application will serve as a unified digital platform for students, providing seamless access to academic schedules, examinations, events, administrative services, fee management, and all essential university resources currently available through the ORTUS web portal.

The prototype will be developed using Flutter for cross-platform mobile development (iOS & Android), following a mock-first architecture that mirrors the existing ORTUS portal functionality. The design will faithfully replicate RTU's brand identity - featuring the signature deep green color palette, FF Mark Pro typography influence, and the clean engineering-focused aesthetic that defines the university's visual language.

The goal is to deliver a fully functional prototype within 8 weeks that demonstrates the complete user experience, validates the technical approach, and positions our team for a production contract with RTU.

## Key Objectives

Replicate RTU website's visual identity and brand language in a mobile-native experience

Demonstrate all core student-facing features from the ORTUS portal in mobile format

Build a scalable architecture ready for real API integration post-contract

Deliver a polished, presentation-ready prototype that showcases production quality

Support both English and Latvian languages from the start

# 2. Project Overview & Scope

## Current State Analysis

RTU currently operates the ORTUS portal (Open Riga Technical University Services), described as the most modern and multifunctional university portal in the Baltic region. Launched in 2007, it serves over 30,000 users and provides unified access to student services including e-learning, class schedules, grade tracking, payment management, and administrative services.

However, ORTUS is primarily web-based and lacks a dedicated mobile application. Students must navigate the full web portal on mobile browsers, leading to a suboptimal experience for on-the-go access to critical academic information.

## Scope of Prototype

| Category | In Scope | Out of Scope |
| --- | --- | --- |
| Authentication | Login/logout UI, biometric mock, session management | Real ORTUS SSO integration |
| Schedule | Class timetable, room details, professor info, week/day views | Real-time schedule sync |
| E-Learning | Course listing, material browser, assignment tracker | LMS integration (Moodle) |
| Grades | Grade dashboard, GPA calculator, semester breakdown | Real grade pull from ORTUS |
| Events | University events calendar, notifications, RSVP | Event creation/admin panel |
| Fees & Payments | Invoice display, payment history, fee breakdown | Payment gateway integration |
| Admin Services | Document requests, FAQ, service center info | Backend ticket processing |
| Library | Catalog search, availability, opening hours | Real library system integration |
| Campus Map | Interactive map, building finder, room locator | Indoor navigation |
| Notifications | Push notification UI, preference center | Real push notification server |
| Profile | Student profile, settings, language toggle | Data sync with ORTUS |

# 3. RTU Brand & Design Reference Strategy

## 3.1 RTU Visual Identity Analysis

RTU underwent a major visual identity overhaul designed by the agency "Teika". The modernized brand transitions from a fragmented system (where each faculty had its own identity) to a unified brand. The design is characterized by clean lines, mathematical accuracy, and laconism - reflecting the essence of engineering.

### Brand Colors

| Color | Usage | Approximate Hex | Application in App |
| --- | --- | --- | --- |
| RTU Deep Green | Primary brand color, decades-old identity | #005C3A | Primary buttons, headers, navigation bar, app bar |
| Dark Green | Secondary accent | #003D26 | Active states, selected tabs, emphasis elements |
| Light Green | Background accent | #E8F5E9 | Card backgrounds, section dividers, subtle highlights |
| White | Clean backgrounds | #FFFFFF | Main content background, card surfaces |
| Near Black | Text and contrast | #1A1A2E | Body text, headings, icons |
| Medium Gray | Secondary text | #666666 | Descriptions, timestamps, placeholder text |
| Light Gray | Borders and dividers | #E0E0E0 | Separators, inactive elements, input borders |

### Typography

RTU uses "FF Mark Pro" as their primary typeface - a technical, modern, readable font family. Since FF Mark Pro is a commercial font, for the mobile app we will:

Use Google's "Inter" font as the closest open-source alternative (geometric, technical, highly readable)

Match the weight hierarchy: Light for body, Medium for labels, Bold for headings, Black for display

If RTU provides a license for FF Mark Pro, swap it in via Flutter's custom font system

### Design Principles (Derived from RTU Brand)

Engineering Precision: Clean grid layouts, consistent spacing, mathematical alignment

Minimal & Functional: No decorative elements - every UI component serves a purpose

Information Hierarchy: Clear visual hierarchy with generous whitespace

Accessibility: High contrast ratios, touch-friendly targets (min 48dp), readable font sizes

Bilingual Ready: UI designed to accommodate both English and Latvian text lengths

## 3.2 Website Reference Extraction Process

To faithfully replicate RTU's web design in the mobile app, we will follow a systematic extraction process:

### Step 1: Visual Audit of rtu.lv

Screenshot every major page section at multiple viewport sizes

Document all color values using browser DevTools (computed styles)

Extract exact font sizes, weights, line heights, and letter spacing

Map all spacing values (margins, paddings) to establish a spacing scale

Catalog all icons and their SVG sources

### Step 2: Component Inventory

Navigation patterns (top nav, side menu, breadcrumbs)

Card designs (news cards, event cards, info cards)

Button styles (primary, secondary, text, icon buttons)

Form elements (inputs, dropdowns, checkboxes, date pickers)

Table and list styles used for schedules and grades

Modal and dialog patterns

### Step 3: Design Token Creation

All extracted values will be codified into a Flutter theme system:

Colors: ThemeData with primary, secondary, surface, error, and custom colors

Typography: TextTheme with display, headline, title, body, and label styles

Spacing: A consistent scale (4, 8, 12, 16, 24, 32, 48, 64)

Border radius: Consistent rounding values across components

Elevation/shadows: Material 3 elevation tokens mapped to RTU's depth system

# 4. Technology Stack

## Frontend (Mobile App)

| Technology | Version | Purpose |
| --- | --- | --- |
| Flutter | 3.x (latest stable) | Cross-platform UI framework (iOS + Android) |
| Dart | 3.x | Programming language |
| Riverpod | 2.x | State management (scalable, testable, production-ready) |
| GoRouter | Latest | Declarative routing with deep linking support |
| Dio | Latest | HTTP client for API communication |
| Hive / Isar | Latest | Local storage for offline caching |
| Flutter Localizations | Built-in | English + Latvian language support |
| Google Fonts (Inter) | Latest | Typography closest to FF Mark Pro |
| flutter_svg | Latest | SVG rendering for icons and illustrations |
| table_calendar | Latest | Calendar widget for schedule and events |
| fl_chart | Latest | Charts for grade analytics and dashboards |

## Backend (Mock Server)

| Technology | Purpose |
| --- | --- |
| Node.js + Express | Lightweight mock API server |
| JSON files | Mock data storage (structured like real ORTUS responses) |
| Firebase (optional) | Push notifications prototype and auth simulation |
| Docker | Containerized deployment for demo consistency |

## Development Tools

| Tool | Purpose |
| --- | --- |
| Figma | UI/UX design and prototyping (before coding) |
| Git + GitHub | Version control and collaboration |
| GitHub Actions | CI/CD for automated builds and testing |
| Fastlane | Automated iOS/Android build and deployment |
| Flutter DevTools | Performance profiling and debugging |

# 5. Application Architecture

## 5.1 Clean Architecture (Feature-First)

The application follows Clean Architecture principles with a feature-first folder structure. This ensures each feature module is self-contained, testable, and can be developed in parallel by different team members.

Project Structure:

lib/
├── core/
│   ├── theme/              # RTU theme, colors, typography
│   │   ├── rtu_colors.dart
│   │   ├── rtu_typography.dart
│   │   └── rtu_theme.dart
│   ├── constants/          # App-wide constants
│   ├── network/            # Dio client, interceptors
│   ├── storage/            # Local DB helpers
│   ├── localization/       # EN/LV translations
│   └── widgets/            # Shared widgets (RTU card, button, etc.)
├── features/
│   ├── auth/
│   │   ├── data/           # Repository implementations, models
│   │   ├── domain/         # Entities, repository interfaces
│   │   └── presentation/   # Screens, widgets, providers
│   ├── schedule/
│   ├── grades/
│   ├── events/
│   ├── elearning/
│   ├── fees/
│   ├── admin_services/
│   ├── library/
│   ├── campus_map/
│   ├── notifications/
│   └── profile/
├── navigation/
│   ├── app_router.dart     # GoRouter configuration
│   └── bottom_nav.dart     # Bottom navigation bar
└── main.dart

## 5.2 Data Flow Architecture

The app uses a Repository Pattern with a mock-first approach. Each feature has:

Data Layer: Repository implementations that currently read from local JSON mock data

Domain Layer: Abstract repository interfaces and entity models (business logic)

Presentation Layer: UI screens and Riverpod state management

When real APIs become available post-contract, only the Data Layer implementations need to change. The Domain and Presentation layers remain untouched. This is the key architectural decision that makes the prototype directly upgradeable to production.

## 5.3 Navigation Architecture

The app uses a bottom navigation bar with 5 primary destinations:

| Tab | Icon | Primary Content | Sub-Navigation |
| --- | --- | --- | --- |
| Home | Dashboard | Today's overview, quick actions, announcements | None (single screen) |
| Schedule | Calendar | Weekly timetable, class details | Day/Week toggle, filter by course |
| Academics | Book | Grades, E-learning, Exams | Tab bar: Grades ¦ Courses ¦ Exams |
| Services | Grid | Fees, Admin, Library, Map | Grid of service cards |
| Profile | Person | Student info, settings, notifications | Settings sub-pages |

# 6. Feature Modules Breakdown

## 6.1 Home Dashboard

The landing screen provides a personalized daily overview for the student.

Greeting with student name and current date/time

Today's schedule summary (next 3 upcoming classes)

Quick action cards: "View Full Schedule", "Check Grades", "Pay Fees"

University announcements carousel (latest 5 news items)

Upcoming events preview (next 3 events)

Unread notification badge counter

## 6.2 Class Schedule

Full academic timetable with multiple view options.

Week view: 7-day grid showing all classes with color-coded subjects

Day view: Detailed timeline for selected day

Class detail card: Subject name, professor, room number, building, time

Current/next class highlight with countdown timer

Filter by semester, course, or professor

Export schedule to device calendar (iCal format)

Tap room number to open campus map with directions

## 6.3 Grades & Academic Performance

Semester-wise grade breakdown with course name, credits, and grade

GPA calculator with visual chart (line chart showing GPA trend)

Current semester progress vs. required credits

Grade distribution analytics (pie chart by grade letter)

Tap any course for detailed assessment breakdown (midterm, final, projects)

Exportable transcript view

## 6.4 E-Learning Hub

Course catalog with enrolled courses prominently displayed

Course detail page: syllabus, materials, assignments, announcements

Assignment tracker with due dates, submission status

Material browser: PDFs, slides, videos organized by week/topic

Offline download support for study materials

Assignment submission status indicator (submitted, graded, pending)

## 6.5 Events & Activities

University events calendar with month/week/list views

Event categories: Academic, Sports, Cultural, Career, Student Council

Event detail page: time, location, description, organizer, RSVP

Bookmark/save events to personal calendar

Push notification reminders for bookmarked events

Filter events by category, date range, or faculty

## 6.6 Fees & Financial Services

Current balance and payment due dates prominently displayed

Invoice history with downloadable PDF invoices

Fee breakdown: tuition, dormitory, library, other charges

Payment status tracking (paid, pending, overdue)

Scholarship information display

Payment method placeholder (ready for gateway integration)

## 6.7 Administrative Services

Service catalog: document requests, certificates, transcripts

Student Service Center info: hours, location, contact

Digital document request forms

Request status tracking (submitted, processing, ready)

FAQ section with searchable knowledge base

Contact directory: departments, offices, key personnel

## 6.8 Library Services

Library catalog search with filters (author, subject, year)

Book availability status and location

Opening hours for all library branches

Study room availability and booking interface

Digital resources and e-journal access links

Current loans and return date reminders

## 6.9 Campus Map

Interactive campus map with building markers

Building directory with floor plans

Room search by room number

Points of interest: cafeteria, parking, ATM, copy center

Directions from current location to any building

Accessibility routes highlighted

## 6.10 Notifications Center

Centralized notification feed (all types)

Categories: Academic, Financial, Events, Administrative, System

Read/unread status with visual indicators

Notification preferences (toggle by category)

Deep linking: tap notification to go to relevant screen

# 7. Data & API Strategy (Mock-First Approach)

Since we do not yet have access to RTU's ORTUS APIs, we will build the prototype with a mock-first architecture. This means every screen works with realistic but simulated data, and the architecture is designed so that swapping mock data for real API calls requires changing only the repository implementations.

## Mock Data Strategy

Create realistic JSON datasets mirroring expected ORTUS response structures

Use actual RTU faculty names, building names, and course codes for authenticity

Generate 2 full semesters of mock schedule data

Create 50+ mock courses with realistic Latvian and English names

Generate grade data across multiple semesters for analytics demos

Include real RTU event types and campus locations

## API Interface Design

Even without real APIs, we design the interface contracts (abstract repository interfaces) based on what ORTUS likely exposes. This includes:

| API Endpoint (Designed) | Data Type | Mock Source |
| --- | --- | --- |
| /api/auth/login | Authentication token | Hardcoded test credentials |
| /api/student/profile | Student details | JSON file with student data |
| /api/schedule/{semester} | Class timetable | Generated schedule JSON |
| /api/grades/{semester} | Grade records | Multi-semester grade data |
| /api/courses/enrolled | Course list | Course catalog JSON |
| /api/events | University events | Events with real RTU types |
| /api/fees/invoices | Payment records | Invoice history JSON |
| /api/library/search | Book catalog | Library items JSON |
| /api/notifications | Notification feed | Mixed notification types |
| /api/services/requests | Service tickets | Request status data |

# 8. Sprint Plan (8 Weeks)

The development is organized into 4 two-week sprints, with clear deliverables at each stage. The team of 2-3 developers will work in parallel tracks to maximize velocity.

## Sprint 1: Foundation & Design System (Weeks 1-2)

Focus: Project setup, RTU theme implementation, core navigation, and design system.

| Task | Assignee | Days | Priority |
| --- | --- | --- | --- |
| Flutter project scaffolding with clean architecture | Dev 1 | 1 | P0 |
| RTU website visual audit and color/typography extraction | Dev 2 | 2 | P0 |
| Implement RTU theme (colors, typography, spacing) in Flutter | Dev 1 | 2 | P0 |
| Design all screens in Figma (wireframes + high-fidelity) | Dev 2/Designer | 5 | P0 |
| Bottom navigation bar + GoRouter setup | Dev 1 | 1 | P0 |
| Shared widget library (RTUCard, RTUButton, RTUTextField, etc.) | Dev 1 | 3 | P0 |
| Setup mock data JSON files and repository interfaces | Dev 3 | 3 | P0 |
| Localization setup (EN/LV) with initial strings | Dev 3 | 1 | P1 |
| CI/CD pipeline setup (GitHub Actions) | Dev 3 | 1 | P1 |

Sprint 1 Deliverable:

Running Flutter app with RTU-branded theme, navigation shell, and reusable component library

## Sprint 2: Core Features - Schedule, Grades, Home (Weeks 3-4)

Focus: Build the three most impactful student-facing features.

| Task | Assignee | Days | Priority |
| --- | --- | --- | --- |
| Home Dashboard screen with today's overview | Dev 1 | 2 | P0 |
| Announcements carousel component | Dev 1 | 1 | P0 |
| Schedule module: week view with color-coded timetable | Dev 2 | 3 | P0 |
| Schedule module: day view and class detail sheet | Dev 2 | 2 | P0 |
| Grades module: semester breakdown list | Dev 3 | 2 | P0 |
| Grades module: GPA chart and analytics dashboard | Dev 3 | 2 | P0 |
| Login/authentication screen with mock flow | Dev 1 | 2 | P0 |
| Onboarding screens (first-time user experience) | Dev 1 | 1 | P1 |
| Pull-to-refresh and loading states across all screens | Dev 2 | 1 | P1 |
| Unit tests for schedule and grades repositories | Dev 3 | 1 | P1 |

Sprint 2 Deliverable:

Working app with login, dashboard, full schedule viewer, and grade analytics

## Sprint 3: Extended Features - Events, E-Learning, Fees (Weeks 5-6)

Focus: Build remaining core features for the complete student experience.

| Task | Assignee | Days | Priority |
| --- | --- | --- | --- |
| Events calendar with month/list views | Dev 1 | 3 | P0 |
| Event detail page with RSVP and bookmark | Dev 1 | 1 | P0 |
| E-Learning course catalog and detail pages | Dev 2 | 3 | P0 |
| Assignment tracker with status indicators | Dev 2 | 2 | P0 |
| Fees module: invoice list and payment history | Dev 3 | 2 | P0 |
| Fees module: fee breakdown and status display | Dev 3 | 1 | P0 |
| Admin services catalog and document request form | Dev 1 | 2 | P0 |
| Notification center with category filters | Dev 3 | 2 | P0 |
| Library search and availability screen | Dev 2 | 2 | P1 |
| Deep linking from notifications to feature screens | Dev 3 | 1 | P1 |

Sprint 3 Deliverable:

Feature-complete app with all student service modules working

## Sprint 4: Polish, Campus Map & Demo Prep (Weeks 7-8)

Focus: Campus map, UI polish, performance optimization, and demo preparation.

| Task | Assignee | Days | Priority |
| --- | --- | --- | --- |
| Campus map with building markers and search | Dev 1 | 3 | P0 |
| Student profile and settings screen | Dev 2 | 2 | P0 |
| Language switcher (EN/LV) with full translation | Dev 3 | 3 | P0 |
| UI polish pass: animations, transitions, micro-interactions | Dev 1 | 2 | P0 |
| Performance optimization (lazy loading, caching) | Dev 2 | 2 | P0 |
| Edge case handling: empty states, error states, offline mode | Dev 2 | 2 | P0 |
| End-to-end testing of all user flows | Dev 3 | 2 | P0 |
| Demo build for iOS and Android (TestFlight / Firebase Distribution) | Dev 1 | 1 | P0 |
| Presentation materials and demo script | All | 2 | P0 |
| Bug fixes and final QA | All | 2 | P0 |

Sprint 4 Deliverable:

Production-quality prototype ready for RTU presentation, with demo builds on both platforms

# 9. Team Allocation & Responsibilities

| Role | Person | Primary Responsibilities |
| --- | --- | --- |
| Team Lead / Architect | Parikshit | Architecture decisions, code reviews, RTU communication, sprint planning, quality gates |
| Developer 1 (Frontend Lead) | TBD | UI implementation, animations, RTU theme system, campus map, home dashboard |
| Developer 2 (Feature Dev) | TBD | Schedule module, e-learning, library, performance optimization, testing |
| Developer 3 (Data/Backend) | TBD | Mock API server, data models, localization, notifications, CI/CD pipeline |

## Parallel Workflow

After Sprint 1 establishes the foundation, the three developers work on different feature modules simultaneously. Daily standups (15 min) ensure alignment. Code reviews are mandatory before merging to the main branch. Parikshit acts as the architectural gatekeeper and handles all communication with RTU stakeholders.

# 10. Website-to-App Theme Extraction Process

This section details the exact technical process for extracting RTU's web design and translating it into a Flutter mobile theme.

## Step 1: Automated Style Extraction

Use browser DevTools on rtu.lv to systematically extract all design tokens:

Open Chrome DevTools > Elements > Computed Styles on every major component

Use the "CSS Overview" panel to get a complete color palette used across the site

Extract all font-family, font-size, font-weight, and line-height values

Document all box-shadow, border-radius, and transition values

Screenshot the responsive breakpoints (mobile, tablet, desktop)

## Step 2: Figma Design System Creation

Convert extracted values into a structured Figma design system:

Create a color palette page with all extracted colors + RTU brand green variants

Build a typography scale page with all text styles

Design all reusable components (buttons, cards, inputs, headers) as Figma components

Create mobile screen designs for every feature at 375x812 (iPhone) and 360x740 (Android)

Include both light theme and potential dark theme variations

## Step 3: Flutter Theme Implementation

Translate the Figma design system into Flutter code:

// rtu_colors.dart
class RTUColors {
  static const Color primary = Color(0xFF005C3A);       // RTU Deep Green
  static const Color primaryDark = Color(0xFF003D26);    // Dark Green
  static const Color primaryLight = Color(0xFFE8F5E9);   // Light Green
  static const Color surface = Color(0xFFFFFFFF);         // White
  static const Color onSurface = Color(0xFF1A1A2E);       // Near Black
  static const Color secondary = Color(0xFF666666);        // Medium Gray
  static const Color divider = Color(0xFFE0E0E0);         // Light Gray
  static const Color error = Color(0xFFD32F2F);            // Error Red
  static const Color success = Color(0xFF2E7D32);          // Success Green
}

// rtu_theme.dart
ThemeData rtuTheme() => ThemeData(
  useMaterial3: true,
  colorScheme: ColorScheme.light(
    primary: RTUColors.primary,
    onPrimary: Colors.white,
    secondary: RTUColors.primaryDark,
    surface: RTUColors.surface,
    onSurface: RTUColors.onSurface,
  ),
  textTheme: GoogleFonts.interTextTheme(),
  appBarTheme: AppBarTheme(
    backgroundColor: RTUColors.primary,
    foregroundColor: Colors.white,
    elevation: 0,
  ),
);

## Step 4: Component-by-Component Matching

Map each web component to its mobile equivalent (e.g., web header -> app bar)

Adapt desktop layouts to mobile patterns (e.g., multi-column -> stacked/tabbed)

Preserve the "feel" while optimizing for touch interactions

Ensure RTU logo placement and sizing follows brand guidelines

# 11. Quality Assurance & Testing Strategy

| Testing Type | Tools | Coverage Target | When |
| --- | --- | --- | --- |
| Unit Tests | flutter_test, mockito | 80%+ on business logic and repositories | Every PR |
| Widget Tests | flutter_test | All shared widgets and critical screens | Every sprint |
| Integration Tests | integration_test package | Core user flows (login, schedule, grades) | Sprint 3-4 |
| UI/UX Review | Manual + Figma comparison | Every screen matches Figma design | Every sprint |
| Performance | Flutter DevTools | <16ms frame time, <2s cold start | Sprint 4 |
| Accessibility | Semantics checker, TalkBack/VoiceOver | WCAG 2.1 AA compliance | Sprint 4 |
| Device Testing | Physical devices + emulators | Top 5 Android + iOS 15/16/17 | Sprint 3-4 |

# 12. Deliverables & Milestones

| Milestone | Week | Deliverable | Stakeholder Checkpoint |
| --- | --- | --- | --- |
| M1: Foundation | Week 2 | Running app shell with RTU theme, navigation, component library | Internal review |
| M2: Core MVP | Week 4 | Login + Dashboard + Schedule + Grades fully functional | Demo to team |
| M3: Feature Complete | Week 6 | All 10 feature modules implemented and integrated | Internal QA sign-off |
| M4: Prototype Ready | Week 8 | Polished app on TestFlight + Firebase, presentation materials | RTU Presentation |

## Final Prototype Package for RTU

iOS build via TestFlight (installable on RTU stakeholders' iPhones)

Android build via Firebase App Distribution (installable APK/AAB)

Figma design file with complete design system

Technical architecture document (this document, updated)

Demo video walkthrough (3-5 minutes)

Source code repository access (optional, for technical evaluation)

# 13. Risk Assessment & Mitigation

| Risk | Impact | Probability | Mitigation |
| --- | --- | --- | --- |
| RTU website redesign during development | High | Low | Extract tokens early in Sprint 1; use abstracted theme that can be updated quickly |
| ORTUS API structure differs significantly from assumptions | Medium | Medium | Repository pattern isolates data layer; only data models need updating |
| FF Mark Pro font licensing issues | Low | Medium | Inter font as fallback is visually similar; swap is a 1-line change |
| Team member availability issues | Medium | Low | Modular architecture allows any developer to pick up any feature |
| iOS/Android platform-specific bugs | Medium | Medium | Test on real devices from Sprint 2; use Flutter's platform-adaptive widgets |
| Scope creep from RTU feedback | High | Medium | Clear scope document (Section 2); defer additions to post-contract backlog |
| Performance issues with complex schedule views | Medium | Low | Use lazy loading, virtualized lists; profile in Sprint 4 |

# 14. Post-Prototype Roadmap

Upon securing the production contract with RTU, the following phases will transform the prototype into a production application:

## Phase 1: API Integration (4-6 weeks)

Integrate with ORTUS authentication (SSO/OAuth)

Connect all data repositories to real ORTUS API endpoints

Implement real-time schedule and grade synchronization

Set up production push notification infrastructure

## Phase 2: Advanced Features (4-6 weeks)

Payment gateway integration for fee payments

Real-time chat/messaging with professors and admin

Document upload for assignment submissions

QR code attendance tracking

Indoor navigation for campus buildings

## Phase 3: Scale & Optimize (Ongoing)

Performance optimization for 30,000+ concurrent users

Analytics dashboard for RTU administration

Faculty-specific features and customizations

Apple Watch / Wear OS companion app for quick schedule checks

AI-powered features: smart study planner, exam preparation assistant

This development plan demonstrates our team's thorough understanding of RTU's ecosystem, technical expertise in cross-platform mobile development, and commitment to delivering a prototype that truly serves the needs of RTU's 30,000+ students. We are ready to begin immediately upon approval.