RIGA TECHNICAL UNIVERSITY

Digital Platform Prototype

Project Roadmap

Mobile Application + Website + Production Deployment

Prepared for: Riga Technical University (RTU)

Prepared by: Development Team

Date: March 23, 2026

Version: 1.0

Classification: Confidential

# Table of Contents

1. Executive Summary

2. Project Overview & Scope

3. System Architecture

4. Technology Stack

5. Development Phases & Timeline

5.1 Phase 1: Foundation & Setup (Weeks 1–2)

5.2 Phase 2: Core Features — Mobile App (Weeks 3–4)

5.3 Phase 3: Website Development (Weeks 5–6)

5.4 Phase 4: Integration & Polish (Weeks 7–8)

5.5 Phase 5: Production Deployment (Weeks 9–10)

6. Team Allocation & Responsibilities

7. RTU Integration Strategy (ORTUS)

8. Production Infrastructure

9. Quality Assurance & Testing

10. Risk Assessment & Mitigation

11. Milestones & Deliverables

12. Post-Launch & Maintenance

# 1. Executive Summary

This roadmap outlines the complete development lifecycle for the Riga Technical University (RTU) digital platform prototype — a unified system comprising a cross-platform mobile application (iOS and Android), a full-featured university website, and a shared backend infrastructure. The project aims to modernize RTU’s digital presence by complementing the existing ORTUS portal with a modern, mobile-first experience for 14,500+ students, faculty, and staff.

The prototype is designed as a mock-first architecture, allowing the team to demonstrate full functionality immediately while enabling a seamless transition to live ORTUS API integration post-contract approval. The development follows a 10-week sprint plan with 2–3 developers, divided into five clear phases from foundation to production deployment.

| Timeline | Team Size | Deliverables | Target Users |
| --- | --- | --- | --- |
| 10 Weeks | 2–3 Developers | 3 Products | 14,500+ Students |

# 2. Project Overview & Scope

The RTU Digital Platform consists of three interconnected products that share a single backend and design system:

### 2.1 Flutter Mobile App (iOS + Android)

A cross-platform mobile application built with Flutter, providing students with on-the-go access to their academic life:

Student Dashboard — personalized home screen with greeting, upcoming classes, quick actions, and announcements

Schedule — interactive weekly/daily class schedule with day selector, class details, room/building info

Academics — grades by semester, GPA tracking (Latvian 1–10 scale), course enrollment status

Services — library access, fee payments, student ID, document requests

Events — university events calendar with categories and registration

Profile — student info, settings, language toggle (LV/EN), notifications, sign out

Push Notifications — grade updates, schedule changes, payment reminders

### 2.2 Next.js Website

A server-rendered website built with Next.js 14 (App Router), covering both the public-facing university presence and the authenticated student portal:

Public Pages: Homepage (hero, stats, faculties, news), About RTU, Admissions (process, fees, deadlines), Faculties listing, Research highlights, News feed, Events calendar

Student Portal: Dashboard (mirroring mobile), Schedule viewer, Academic record / grades, Tuition & fee management

SEO & Performance: Server-side rendering for public pages, ISR (Incremental Static Regeneration) for news/events, optimized Core Web Vitals

### 2.3 Shared Node.js Backend

A unified Express.js + TypeScript API server that provides data to both mobile and web clients:

RESTful API with 10+ route modules (auth, student, schedule, grades, events, fees, courses, library, notifications, public)

Mock data layer with authentic RTU data — Latvian names, Kīpsala campus buildings, real course code formats

Repository pattern for clean mock-to-production swap — only the data layer changes

CORS configured for all client origins (Next.js :3000, Flutter web :8080, Android emulator)

# 3. System Architecture

The architecture follows a clean separation of concerns with three client applications connecting to a shared backend:

| Flutter Mobile App | Next.js Website | Shared Backend |
| --- | --- | --- |
| iOS + Android Dart / Flutter 3.x Riverpod + GoRouter Dio HTTP Client | Public + Portal TypeScript / React 18 App Router + SSR Tailwind CSS | REST API Node.js + Express TypeScript Mock → ORTUS API |

### Data Flow

All three clients communicate with the shared backend via RESTful HTTP. The backend currently serves mock data from an in-memory data module. Post-contract, the mock data layer is replaced with ORTUS API integration — the route handlers and response formats remain identical, ensuring zero client-side changes.

### Key Architecture Decisions

| Decision | Rationale |
| --- | --- |
| Repository Pattern | Abstract interfaces in domain layer, mock implementations now, real API later — only data layer changes |
| Flutter for Mobile | Single codebase for iOS + Android, hot reload for fast prototyping, Dart’s type safety |
| Next.js for Web | SSR for SEO (critical for university public pages), App Router for modern patterns, React ecosystem |
| Shared Express Backend | Single source of truth for both clients, consistent API contracts, easy ORTUS integration later |
| Mock-First Architecture | Full prototype functionality without ORTUS API access, demonstrates UI/UX immediately |

# 4. Technology Stack

### Mobile Application

| Technology | Purpose |
| --- | --- |
| Flutter 3.x + Dart | Cross-platform UI framework |
| Riverpod | State management (FutureProvider, StateProvider) |
| GoRouter | Declarative routing with ShellRoute for bottom nav |
| Dio | HTTP client for API communication |
| Google Fonts (Inter) | Typography (fallback for FF Mark Pro) |
| table_calendar | Calendar widget for schedule and events |
| fl_chart | Charts for GPA visualization |
| shimmer | Loading placeholder animations |

### Website

| Technology | Purpose |
| --- | --- |
| Next.js 14 (App Router) | React framework with SSR/SSG/ISR |
| TypeScript | Type-safe development |
| Tailwind CSS | Utility-first styling with RTU brand tokens |
| Lucide React | Icon library |

### Shared Backend

| Technology | Purpose |
| --- | --- |
| Node.js + Express | API server framework |
| TypeScript | Type-safe backend development |
| CORS / Helmet / Morgan | Security headers, logging, cross-origin support |

### RTU Brand Design Tokens

| Token | Value | Usage |
| --- | --- | --- |
| Primary Green | #005C3A | Buttons, headers, active states |
| Dark Green | #003D26 | Footer, gradients, emphasis |
| Light Green | #007A4D | Hover states, secondary actions |
| Green Surface | #E8F5E9 | Backgrounds, cards, subtle tints |
| Font: Inter | Fallback for FF Mark Pro | All UI text (swap-ready) |
| Border Radius | 12px | Cards, buttons, containers |

# 5. Development Phases & Timeline

The project follows a 10-week sprint plan divided into 5 phases. Each phase has specific deliverables, success criteria, and demo checkpoints.

| Phase | Focus | Weeks | Status |
| --- | --- | --- | --- |
| Phase 1 | Foundation & Setup | Weeks 1–2 | ✅ Complete |
| Phase 2 | Core Features — Mobile App | Weeks 3–4 | ✅ Complete |
| Phase 3 | Website Development | Weeks 5–6 | 🔄 In Progress |
| Phase 4 | Integration & Polish | Weeks 7–8 | ⏳ Upcoming |
| Phase 5 | Production Deployment | Weeks 9–10 | ⏳ Upcoming |

## 5.1 Phase 1: Foundation & Setup (Weeks 1–2)

Establish the project infrastructure, design system, and architecture for all three products.

### Week 1: Project Setup & Architecture

Initialize Flutter project (rtu_app/) with clean architecture folder structure

Initialize Node.js backend (rtu_backend/) with Express + TypeScript

Initialize Next.js website (rtu_web/) with App Router + Tailwind

Set up Git repository with branching strategy (main / develop / feature/*)

Configure CI/CD pipelines (GitHub Actions)

### Week 2: Design System & Mock Data

Build RTU theme system in Flutter (colors, typography, spacing, Material 3 ThemeData)

Build RTU Tailwind config for web (brand tokens, shadows, border radius)

Create shared reusable widget library (RTUCard, RTUButton, RTUShimmer, etc.)

Build comprehensive mock data with authentic RTU content (Latvian names, Kīpsala buildings, real course codes)

Implement backend API routes for all 10+ modules

Deliverables: Running dev environments for all 3 projects, shared design system, complete mock data, backend API serving data

Demo: Show RTU-branded Flutter app shell with navigation, themed website scaffold, and API returning mock data

## 5.2 Phase 2: Core Features — Mobile App (Weeks 3–4)

Build all student-facing features in the Flutter mobile application.

### Week 3: Primary Student Features

Splash screen with animated RTU logo and auto-login flow

Login screen (ORTUS-style form with pre-filled demo credentials)

Home dashboard with gradient header, quick actions grid (3×2), upcoming classes, announcements carousel

Schedule screen with Mon–Fri day selector, timeline-connected class cards, bottom sheet details

Academics screen with tabbed view (Grades / Courses / Exams), GPA card, semester grade lists

### Week 4: Secondary Features & Navigation

Services screen with 3×3 grid (Library, Fees, Student ID, Documents, Map, IT Support)

Events screen with category filters and event detail view

Profile screen with settings groups, language toggle, notification preferences, sign out

Notifications screen with read/unread states, categorized feed

Bottom navigation with 5 tabs (Home, Schedule, Academics, Services, Profile) using ShellRoute

Deliverables: Fully navigable Flutter app with all student features, loading states, empty states, error handling

Demo: Complete walkthrough of the mobile app on both iOS simulator and Android emulator

## 5.3 Phase 3: Website Development (Weeks 5–6)

Build the complete RTU website with both public-facing pages and the student portal.

### Week 5: Public Website Pages

Homepage — hero section, stats bar, faculties grid, news feed, events sidebar, CTA card, portal banner

Responsive Navbar with top bar, logo, navigation links, mobile hamburger menu, “Apply Now” CTA

Footer with 5-column layout (brand, university links, admissions, students, contact)

About RTU page — mission/vision, stats, historical timeline (1862–2026), leadership profiles

Admissions page — 6-step application process, tuition table, deadlines, required documents

Faculties page — all 8 RTU faculties with deans, student counts, programs, research highlights

Research, News, and Events pages with category filters and featured content

### Week 6: Student Portal (Web)

Portal dashboard — student profile header, quick actions, today’s schedule, notifications, semester progress

Schedule page — interactive day selector, class cards with professor names, room numbers, course codes

Grades page — expandable semester view, course tables, GPA tracking, credit progress

Fees page — payment summary, upcoming payments, payment history, bank details

Connect all portal pages to shared backend API via Next.js proxy rewrites

Deliverables: Fully functional website with 10+ pages, responsive design, connected to shared backend

Demo: Full website walkthrough showing public pages + authenticated portal experience

## 5.4 Phase 4: Integration & Polish (Weeks 7–8)

Connect all components, polish UI/UX, and prepare for production readiness.

### Week 7: Cross-Platform Integration

Connect Flutter app to shared backend (replace local JSON mock data with Dio HTTP client pointing to rtu_backend)

Implement authentication flow end-to-end (login → token storage → API auth headers → session management)

Add pull-to-refresh, infinite scroll, and offline caching for mobile

Implement push notification infrastructure (Firebase Cloud Messaging)

Add deep linking between web and mobile (app.rtu.lv → opens native app if installed)

Cross-browser testing for website (Chrome, Firefox, Safari, Edge)

### Week 8: UI/UX Polish & Accessibility

Loading states, error states, and empty states for all screens (both mobile and web)

Animation polish — page transitions, micro-interactions, skeleton loading

Responsive design audit — test website at all breakpoints (mobile, tablet, desktop)

Accessibility audit — WCAG 2.1 AA compliance (color contrast, keyboard nav, screen reader, ARIA labels)

Latvian language support — LV/EN toggle with all UI strings localized

Performance optimization — image lazy loading, code splitting, bundle analysis

RTU brand consistency check — verify all colors, fonts, spacing match brand guidelines

Deliverables: Integrated platform with mobile app connected to backend, polished UI, accessibility compliance

Demo: End-to-end user journey: login on mobile → view schedule → check grades on web → receive notification

## 5.5 Phase 5: Production Deployment (Weeks 9–10)

Deploy all three products to production infrastructure and prepare for university handover.

### Week 9: Infrastructure & Deployment

Set up production environment on cloud provider (AWS / DigitalOcean / RTU’s infrastructure)

Configure PostgreSQL database for production data storage (replacing in-memory mock data)

Deploy backend API to production server with PM2 / Docker container

Deploy Next.js website to Vercel or self-hosted Nginx with SSL

Submit Flutter app to Apple App Store (TestFlight) and Google Play Store (Internal Testing)

Set up monitoring and alerting (Sentry for errors, Uptime Robot for availability)

Configure CDN for static assets (images, fonts, icons)

### Week 10: Testing, Handover & Presentation

End-to-end testing across all platforms (iOS, Android, web desktop, web mobile)

Load testing the backend API (target: handle 30,000+ concurrent users matching RTU’s student body)

Security audit — input validation, SQL injection prevention, XSS protection, rate limiting

Create comprehensive technical documentation (API docs, deployment guides, architecture diagrams)

Prepare demo presentation for RTU stakeholders

Create user guide for students and faculty

Handover meeting with RTU IT department

Deliverables: Production-deployed platform, app store builds, documentation, demo presentation

Demo: Live production demo with RTU stakeholders accessing the app and website in real-time

# 6. Team Allocation & Responsibilities

The project is structured for a lean team of 2–3 developers with a team lead overseeing all workstreams:

| Role | Focus Area | Technologies | Phases |
| --- | --- | --- | --- |
| Team Lead | Architecture, code review, ORTUS integration, demos | All | All |
| Developer 1 | Flutter mobile app, state management | Flutter, Dart, Riverpod | Phases 1–4 |
| Developer 2 | Next.js website, shared backend, API | Next.js, TypeScript, Express | Phases 1–4 |
| Dev 3 (optional) | UI polish, testing, docs, DevOps | Testing, CI/CD, Docker | Phases 4–5 |

### Daily Workflow

Standup (15 min) — What was done yesterday, what’s planned today, any blockers

Feature branches — feature/* branches merged to develop via pull request

Code review — All PRs reviewed by team lead before merge

Sprint demo (biweekly) — Show completed features to team and stakeholders

Retrospective (biweekly) — What went well, what to improve

# 7. RTU Integration Strategy (ORTUS)

ORTUS (Open Riga Technical University Services) is the existing web portal used by 30,000+ users. The integration strategy ensures a smooth transition from prototype to production without disrupting the existing system.

### Mock-to-Production Transition

The Repository Pattern is the cornerstone of the integration strategy. During the prototype phase, all data comes from mock repositories. Post-contract, only the data layer needs to change:

| Layer | Prototype (Now) | Production (Post-Contract) |
| --- | --- | --- |
| Domain | Abstract interfaces (unchanged) | Abstract interfaces (unchanged) |
| Data | MockScheduleRepository reads from JSON/memory | OrtusScheduleRepository calls ORTUS REST API |
| Presentation | UI components (unchanged) | UI components (unchanged) |
| Backend | In-memory mock-data.ts | PostgreSQL + ORTUS API proxy |

### ORTUS API Integration Checklist

Obtain ORTUS API documentation and access credentials from RTU IT

Map ORTUS data models to existing app entities (Student, ClassSession, Grade, etc.)

Implement OAuth2/SAML authentication flow for RTU SSO (single sign-on)

Build API adapter layer that transforms ORTUS responses to match existing mock format

Implement data caching layer (Redis) to reduce ORTUS API load

Add error handling for ORTUS API downtime (graceful fallback, retry logic)

Load test the integration under realistic conditions (peak enrollment, exam season)

### RTU-Specific Data Handling

Latvian grading system (1–10 scale) — already implemented with proper color coding

Course codes follow RTU format: DatZ3001, MatZ2001, FizZ1002, ValZ1001

Building names use official RTU names: Kīpsala I, Kīpsala II, DITF, Sports Center

Academic calendar follows Latvian semester structure (Autumn: Sep–Jan, Spring: Feb–Jun)

Multi-language support: Latvian (primary) and English for international students

# 8. Production Infrastructure

### Recommended Architecture

| Component | Technology | Hosting |
| --- | --- | --- |
| Mobile App | Flutter (compiled native) | App Store + Google Play |
| Website | Next.js 14 (SSR) | Vercel or self-hosted Nginx |
| Backend API | Node.js + Express | Docker on AWS EC2 / DigitalOcean |
| Database | PostgreSQL 15+ | AWS RDS or managed instance |
| Cache | Redis | ElastiCache or managed Redis |
| CDN | CloudFront / Cloudflare | Global edge caching |
| Monitoring | Sentry + Grafana | Cloud-hosted |
| CI/CD | GitHub Actions | Auto-deploy on merge to main |

### Environment Strategy

| Environment | Purpose | Data Source |
| --- | --- | --- |
| Development | Local dev with hot reload | Mock data (in-memory) |
| Staging | Pre-production testing | Copy of ORTUS test DB |
| Production | Live for all students | ORTUS API + PostgreSQL |

### Security Requirements

HTTPS everywhere (TLS 1.3) with valid SSL certificates

JWT-based authentication with short-lived access tokens + refresh tokens

GDPR compliance — RTU student data processing under EU regulations

Rate limiting on all API endpoints (100 requests/min per user)

Input validation and sanitization on all user inputs

SQL injection prevention via parameterized queries

Content Security Policy (CSP) headers on website

Regular dependency auditing (npm audit, Snyk)

# 9. Quality Assurance & Testing

| Test Type | Scope | Tools |
| --- | --- | --- |
| Unit Tests | Business logic, utilities, data transforms | Flutter test, Jest |
| Widget Tests | Individual UI components | Flutter widget test |
| Integration Tests | API endpoints return correct data | Supertest, Postman |
| E2E Tests | Full user journeys across platforms | Maestro (mobile), Playwright (web) |
| Performance | Load testing, response times | k6, Lighthouse |
| Accessibility | WCAG 2.1 AA compliance | axe-core, manual audit |
| Security | Vulnerability scanning | OWASP ZAP, npm audit |

### Quality Gates (Must Pass Before Each Phase)

All unit tests passing (target: 80%+ code coverage for business logic)

Zero critical bugs in issue tracker

Lighthouse score > 90 for Performance, Accessibility, Best Practices (website)

All API endpoints return correct status codes and response shapes

No TypeScript/Dart compilation errors

Code review approved by team lead

# 10. Risk Assessment & Mitigation

| Risk | Impact | Likelihood | Mitigation |
| --- | --- | --- | --- |
| No ORTUS API access during prototype | High | Confirmed | Mock-first architecture with Repository Pattern; identical API contracts ensure seamless swap |
| FF Mark Pro font unavailable | Low | High | Using Inter (open-source) with documented swap process; visually similar |
| Timeline pressure (10 weeks) | Medium | Medium | Clear phase milestones, shared backend reduces duplication, biweekly demos |
| ORTUS API differs from mock structure | Medium | Medium | Adapter pattern in backend isolates transformation logic; only data layer changes |
| App Store review delays | Medium | Medium | Submit TestFlight early in Week 9; use web app as fallback demo |
| Performance under load | High | Low | Redis caching, CDN for static assets, database indexing, load testing in Phase 5 |
| GDPR compliance gaps | High | Medium | Data processing audit, consent management, RTU DPO consultation, encryption at rest |

# 11. Milestones & Deliverables

| Week | Milestone | Deliverable | Success Criteria |
| --- | --- | --- | --- |
| 2 | Foundation Complete | Dev environments, design system, mock API | All 3 projects run locally |
| 4 | Mobile App MVP | Flutter app with all student features | Full app walkthrough possible |
| 6 | Website MVP | Next.js site with public + portal pages | All 10+ pages rendering |
| 8 | Integration Complete | Connected platform, polished UI | E2E user journey works |
| 10 | Production Launch | Deployed platform, app store builds, docs | Live demo with RTU |

### Presentation Strategy for RTU

The final demo to RTU stakeholders should follow this structure:

Problem Statement — Show current ORTUS limitations (desktop-only, dated UI, no mobile app)

Solution Overview — Present the unified platform concept (mobile + web + shared backend)

Live Demo — Walk through the mobile app (login → dashboard → schedule → grades → services)

Website Demo — Show public pages (admissions, faculties) + student portal

Technical Architecture — Explain mock-to-production transition (zero client changes needed)

Roadmap & Next Steps — ORTUS API integration timeline, scaling plan, ongoing support model

# 12. Post-Launch & Maintenance

### Ongoing Maintenance Plan

Weekly dependency updates and security patches

Monthly performance review (API response times, app crash rates, web vitals)

Quarterly feature releases aligned with RTU academic calendar

24/7 error monitoring with Sentry alerts

User feedback collection via in-app feedback form and RTU IT helpdesk integration

### Future Feature Roadmap (Post-Contract)

| Priority | Feature | Timeline |
| --- | --- | --- |
| P0 | ORTUS SSO Integration (SAML/OAuth2) | Month 1–2 |
| P0 | Live Schedule & Grades from ORTUS API | Month 2–3 |
| P1 | Push Notifications (FCM + APNs) | Month 3–4 |
| P1 | Campus Map with Indoor Navigation | Month 4–5 |
| P1 | Library Book Search & Reservation | Month 4–5 |
| P2 | Student-to-Student Messaging | Month 5–6 |
| P2 | Course Registration & Enrollment | Month 5–6 |
| P2 | Parking & Transport Information | Month 6–7 |
| P3 | AI-Powered Academic Advisor Chatbot | Month 7–8 |
| P3 | Alumni Network & Career Portal | Month 8–10 |

────────────────────────────────────────────────────────────

End of Document

Prepared with care for Riga Technical University

Development Team | March 2026